## Conference
Updated: [DATE]
Status | Item | Responsible/Delegated To | Status / Notes | Considerations
To Do | [YEAR] Conference Site |  |  | Availability, venue size/capacity for attendees and vendors, housing proximity, parking considerations for attendees and vendors, available discounts for groups or public safety, nearest airport transportation/location, services offered, ADA standards, off-site event opportunities (within 20 min), right-to-work state, union/labor
In Progress | Attendee Activities |  |  | Team or Conference Challenges/Social events, awards for winner(s), proximity to housing/conference center, duration of event and scheduling conflicts, budget and sponsorship opportunities, appropriate for audience
Complete | Audio Video / Technology |  |  | Needs of speakers, needs of social event(s) & banquet, if AV equipment is included in venue price or in addition to, onsite troubleshooting/functionality verification, session recordings
Cancelled | Awards |  |  | Nomination submittals and selection committee (consider outsourcing award winner selection to another state board for objectivity), adequate time allocated for award ceremony based on number of awards/recipients present/videos/speeches, recognizing others who were nominated but not selected, physical award for recipient (plaques, trophies, challenge coins, etc) and ensuring enough time to have them made,
| Banquet |  |  | Dinner, awards & recognition; swearing in of incoming board with script, music/slideshow/pre-recorded videos, prepared speeches/scripts
| Budget/Finance |  |  | Individual budgets for separate committees and a master budget for the conference as a whole; confirming estimates from hotel(s), exhibit center, transportation, catering, and other contractual services; rules for disbursement of funds & signatories; reimbursement rules; established budget timeline and regular review; billing for registration fees; tips, taxes & fees
| Call for Presentations |  |  | Establish clear communication for the presentation timeline: when the Call for Presentations/Papers is open, when it closes, how speakers are selected, and when speakers are selected/notified. Consider using an application to assist with adhering to deadlines/storage/shared access for the selection committee/communication with presenters
| CEU Certificates |  |  | Determine if hours are for the conference as a whole or individual classes attended; follow local rules/regulations for acquiring site codes
| Closing Session |  |  | Timeline / Speaker / Ceremony
| Conference App |  |  | Platform availability; cost; user friendly; newsfeed/photo uploads; administrative access & privileges; included features -- at a minimum should include schedule, session descriptions, and participating vendors. Other features to consider: vendor associated links, presentation slides, registration, exhibit hall layout, and session evaluations. [See Conference Website]
| Conference App Promotion |  |  | Determine timeline for app to be ready by (before / on / after registration opens); utilize listserves for announcing app; create QR codes linking to iOS & android downloads; share on social media, snail mail and flyers
| Conference Bag |  |  | Attendee Commemorative Item (pin, challenge coin, etc): cost, ordering/receiving timeline, quantity. Determine if First Time Attendees receive additional gift and when it is distributed to them.
| Conference Breaks |  |  | Duration (provide enough time for breaks and traveling to next event/class); enough time for attendees to get ready before banquet/awards ceremony; consider a longer break if food is provided
| Conference Committee Dinner |  |  | Recommended before conference kickoff to bring the committee together and celebrate all of the hardwork and collaboration leading up to conference
| After Action Review |  |  | Recommended immediately post-conference and in-person if possible (e.g. Hot Wash Breakfast); encourage committee members to keep a running list of wins/opportunities to review during the AAR
| Conference Website |  |  | If not a joint chapter, recommend using a separate website for the conference; can use the conference app as the primary landing page and in place of a traditional website [See Conference App]. Can include information on: registration, hotel, travel, venue/host location, schedule, vendors, attendee list, etc. Note: ensure all links are accurate and updated and copyright rules are being adhered to
| Decorations & Theme |  |  | Should be determined ahead of advertising for the conference so that advertisements can be branded; consider a chapter engagement piece (members submit ideas/logos/designs); create a theme that is engaging for your attendees (dress up for banquet, items to interact with throughout conference, music, food items, giveaways, & tie side events into the theme for cohesiveness); can ask chapter members for decoration items to be donated
| DJ/Band/Entertainment |  |  | Vet the performer(s); secure the day/time and expectations with contract language; determine A/V needs & crossreference with venue contractual rules/limitations
| Education |  |  | Determine breakout session locations based on anticipated class size, speaker availaibility, duplicate session offerings, venue availability, etc. Up to date speaker biographies and session descriptions. Determine applicable professional development tracks (e.g. Frontline TC, Supervisor/Manager, Technical, Trainer, Wellness, Statewide Updates/Legislative). Determine volunteer(s) to introduce speakers and volunteers to scan badges (if needed). Is there any requirement to provide sponsorship advertisements at the beginning of the session? How will this be coordinated and who will be responsible to ensure this is done for each session?
| Emcee |  |  | Keynote introductions (opening/closing session) & housekeeping items; banquet facilitation; general announcements; time management; sponsor acknowledgements; vendor hall coordination/raffles/announcements; participant engagement
| Exhibit Hall |  |  | Venue space allocation will limit number of exhibitors; power & A/V needs of vendors; facility limitations (e.g., driving vehicles inside, space/door restrictions); fees (storage/handling), timelines & address for drop shipping; established POC for the venue in the exhibit hall; hanging/suspended banners & signs; having a good setup and breakdown schedule that is communicated with the exhibitors; process for assigning booths; how to deal with "suitcasing" when a vendor attends but doesn't have a booth and then solicits attendees and gives out items; CCAM coordination and communication between the chapter and vendors; ensuring payment is made before the vendor sets up in the exhibit hall (set a hard deadline to accept vendor fees by); considering complimentary booths and who qualifies for these
| Fees |  |  | Member & non-member registration; flash/sale day rate and advertisement; day pass rate; banquet/special event registration only; establish who gets reduced or free registration
| First Time Attendee Reception/Recognition |  |  | Established budget; date & time advertisement; special door prizes (including from industry partners); representatives from chapter leadership to welcome new attendees
| Hospitality |  |  | Speaker Ready Room, Snacks, Designated Spaces (Rest & Recharge, Meeting, etc)
| Industry Conference Promotional Items |  |  | Dependent on combined conference; promotional items can be separate from attendee bags (exhibit hall)
| Lanyards / Ribbons for Badges |  |  | Include extra at the Registration Desk; vendor sponsored lanyards; identifying ribbons for new attendees, committee members, professional designations, chapter leaders, fun themes, etc
| Lodging |  |  | Reserving room blocks for not only conference but also any pre-conference events; proximity to classes/exhibit hall; ADA compliance & accessibility considerations; multiple sites depending on number of attendees/vendors and having a backup for overflow; shuttle availability
| Menus |  |  | Tasting opportunities, dietary restrictions (noted at registration and how are they identified by staff); provided snack break(s)
| Name Badges |  |  | Should include attendee name, agency, registration type, QR code to scan in the vendor hall to enter drawings & share contact information; have extra printer & materials at registration desk for on-site registrations or reprints; special event tickets (attached to or distributed with); badge holder; ensure badge holder works with the conference/vendor sponsored lanyard; special identifiers for registration type(s) and their access limitations
| Opening Session |  |  | Timeline / Speaker / Honor Guard
| Pre-Conference Classes |  |  | Opportunities to bundle a pre-conference class with keynote/breakout session; define & determine # of attendees/cost/space & seating
| Promotion |  |  | Social media/website/e-blast/promote at national conference/prior attendee notifications & reminders/snail mail versions particularly for underrepresented ECCs in the area
| Registration Desk |  |  | Staffed hours/after-hours contact(s); pre-registration & on-site registration; general office supplies; extra event tickets if necessary; printed materials (class schedules, session descriptions, etc)
| Safety & Security |  |  | Specified evacuation/safety plan; secure access to vendor floor during and after-hours; health considerations
| Schedule |  |  | Consider travel for your attendees and how this will impact their attendance for opening and closing session(s), e.g. late start for opening session, half day for closing session, etc. Have a paper copy of the schedule at a glance (high level) at the registration desk for attendees who do not have the conference app
| Session Evaluations |  |  | Send out to attendees after conference (through conference app or attendee email listing); can connect to CEU credit to ensure completion of evaluations. Leave evaluations open for approximately one month, compile results and have conference committee review for feedback and future planning
| Session Recordings |  |  | Make sure technology is in place and tested in advance; have a distribution plan and guidelines for retention; determine cost and how attendees can purchase access (before, during or after conference)
| Shuttle |  |  | Designated routes/pick up points; departure & arrival schedule
| Signs for Breakout Sessions |  |  | Schedule information (date/time) & topic; digital vs. physical options (using app as backup)
| Signs for Sponsors, Events, Etc. |  |  | Sign holders/easel (and spares) and ways to connect banners to walls, booths, rafters, etc; digital versus printed versions; check for accuracy and have a way to do corrections on the fly if needed; venue coordination if any A/V needs; ensure sponsorship visibility if part of their sponsorship
| Sponsorship Opportunities |  |  | Consider budget year differences & conference timing; outline benefits and levels of sponsorship; define conference only or year-around sponsorship; vendor sponsorship of banquet staff tips
| Chapter Merchandise Store |  |  | Location (exhibit hall? registration desk?)
| Conference T-Shirts |  |  | Consider making the shirts have longevity (will it be worn outside of this one event?); partner with a local vendor to come onsite and make t-shirts in the vendor hall; cost/budgeted item or for chapter profit
| Vendor/Attendee Social Event |  |  | Dress code/theme/planned activities; Vendor "Speed Dating" opportunity to create connections with commercial partners and the opportunity for more one-on-one demos
| Volunteers |  |  | Determine who is the lead for Volunteers; announce call for volunteers; determine a list of needs for volunteers to fill (pre-, post-, and during conference); have a meeting/training; have a communication platform with accountability for job assignments; define job duties for different volunteers; consider incentives for volunteering (day pass, waived or reimbursed conference registration, etc) and a check-in process for actual participation; identifying shirts/lanyards/badge ribbons
Notes for [YEAR] Conference:
Complete
To Do or Action Needed
In Progress
Not Applicable to Event
Cancelled (Action no longer needed)

## Vendor Tracking
Updated: [DATE]
Reg Status | Space Assignment | Company Name | Sponsor Level | Delivery Needs | Registration Contact Information | On-site Contact Information | Notes | Considerations
Paid |  |  | Diamond |  |  |  |  | Delivery Needs: loading dock, forklift, etc
Pending |  |  | Platinum
Not Registered |  |  | Gold
N/A |  |  | Silver
Bronze
Notes for [YEAR] Conference:
Complete
To Do or Action Needed
In Progress
Not Applicable to Event
Cancelled (Action no longer needed)